## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project:
Week Of:
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
| 1 | Clark |  | Client and server communication with Arshad, client gui using react | continuing working on client gui using react
| 2 | Jigar |  | Server backend (communication and logic) | inetgration of the server component to other components such client gui
| 3 | Arshad |  | Setup react and established communication between server and client that uses react | proper display of evaluation of server on client gui (communication from server to client), socket.io for client
| 4 | Angela |  | creating classes on server side (game logic) and storing data | Testing that game logic works, integration of game logic to other components with Jigar
Final Project Documentation | 5 | All